## Sheet1
App Name: Support 360
Developed by: Arif Mahmud
Supervised by: Nani Gopal Barai
Support by: Nani Gopal Barai
Sponsored by: BJIT Academy
# | Task Module | Features To be implemented | Activities to be done | App Dev(Man Day) | Start Date | End Date
Week 1
1 | Project Initiation | 1.1 Project Definition | 1.1.1 Purpose and goals of the project | 0.25 | 21.01.25 | 21.01.25
|  |  | 1.1.2 Project scope and constraints | 0.25 | 21.01.25 | 21.01.25
|  | 1.2 Project Charter | 1.2.1 Project timeline | 0.25 | 21.01.25 | 22.01.25
|  |  | 1.2.2 Project resources | 0.25 | 21.01.25 | 22.01.25
|  |  | 1.2.3 Project risks and assumptions | 0.5 | 22.01.25 | 22.01.25
|  |  | 1.2.4 Setting up Work Plan | 0.5 | 22.01.25 | 22.01.25
2 | Requirements Analysis | 2.1 Documenting Requirements | 2.1.1 Get requirements from trainers | 0.15 | 23.01.25 | 23.01.25
|  |  | 2.1.2 Validating Requirements | 0.15 | 23.01.25 | 23.01.25
|  | 2.2 Prepare SRS | 2.2.1 Functional Requirements | 0.3 | 23.01.25 | 23.01.25
|  |  | 2.2.2 Non-Functional Requirements | 0.25 | 23.01.25 | 23.01.25
|  |  | 2.2.3 Project Scopes | 0.15 | 23.01.25 | 23.01.25
3 | Design | 3.1 Design Diagram | 3.1.1 Design of Usecase Diagram | 0.15 | 24.01.25 | 24.01.25
|  |  | 3.1.2 Design of Activity Diagram | 0.15 | 24.01.25 | 24.01.25
|  |  | 3.1.3 Design of State Machine Diagram | 0.15 | 24.01.25 | 24.01.25
|  |  | 3.1.4 Design of Sequence Diagram | 0.25 | 24.01.25 | 24.01.25
|  | 3.2 Database Design | 3.2.1 Design of Entity Relationship Diagram | 0.15 | 24.01.25 | 24.01.25
|  |  | 3.2.2 Design of Object Diagram | 0.15 | 24.01.25 | 24.01.25
Week 2
|  | 3.3 Architecture Design | 3.3.1 Deployment Diagram | 0.35 | 27.01.25 | 27.01.25
|  |  | 3.3.2 Defination of System Architechture Interfaces | 0.3 | 27.01.25 | 27.01.25
|  |  | 3.3.3 Design of System Architechture Interfaces | 0.35 | 27.01.25 | 27.01.25
4 | Development | 4.1 Object Development | 4.1.1 Develop and Create Project__c | 0.3 | 28.01.25 | 28.01.25
|  |  | 4.1.2 Develop and Create Resource__c | 0.3 | 28.01.25 | 28.01.25
|  |  | 4.1.3 Development of Case Object | 0.4 | 28.01.25 | 28.01.25
|  |  | 4.1.4 Automate Status changes and Notify the Users on Case__c | 0.5 | 29.01.25 | 29.01.25
|  |  | 4.1.5 Development of Task Object | 0.25 | 29.01.25 | 29.01.25
|  |  | 4.1.6 Create Case Record type | 0.25 | 29.01.25 | 29.01.25
|  | 4.2 Back-End Development | 4.2.1 Approval process on Case Status Change | 0.5 | 30.01.25 | 30.01.25
|  |  | 4.2.2 Due Date Notification | 0.5 | 30.01.25 | 30.01.25
|  |  | 4.2.3 Design Lwc Modal/Popup for Manager Change | 0.6 | 31.01.25 | 31.01.25
|  |  | 4.2.4 Automate Notification to New Manager via Email | 0.4 | 31.01.25 | 31.01.25
Week 3
|  |  | 4.2.5 Generate CSV report with Case details & Project Manager url | 0.5 | 03.02.25 | 03.02.25
|  |  | 4.2.6 Apex Code to generate CSV File with Case details & Project Manager url | 0.5 | 03.02.25 | 03.02.25
|  | 4.3 Dependencies Development | 4.3.1 Change Manager Button in Manager__c object | 0.15 | 04.02.25 | 04.02.25
|  |  | 4.3.2 Develop Reporting Dashboard | 0.6 | 04.02.25 | 04.02.25
|  |  | 4.3.3 Implement Collaboration and Chatter | 0.25 | 04.02.25 | 04.02.25
|  |  | 4.3.4 Security and Access Control | 1 | 05.02.25 | 05.02.25
|  |  | 4.3.5 Custom Layout Development for each Objects | 0.5 | 06.02.25 | 06.02.25
|  |  | 4.3.6 Create Custom Tab | 0.5 | 06.02.25 | 06.02.25
|  |  | 4.3.7 Create Lightning App and Manage all the Dependencies | 1 | 07.02.25 | 07.02.25
Week 4
5 | Testing | 5.1 Unit Testing | 5.1.1 Test plan development | 0.5 | 10.02.25 | 10.02.25
|  |  | 5.1.2 Test case development | 0.5 | 10.02.25 | 10.02.25
|  |  | 5.1.3 Test case execution | 0.5 | 11.02.25 | 11.02.25
|  | 5.2 System Testing | 5.2.1 Test plan development | 0.5 | 11.02.25 | 11.02.25
|  |  | 5.2.2 Test case development | 0.5 | 12.02.25 | 12.02.25
|  |  | 5.2.3 Test case execution | 0.5 | 12.02.25 | 12.02.25
|  | 5.3 User Acceptance Testing | 5.3.1 Test plan development | 0.5 | 13.02.25 | 13.02.25
|  |  | 5.3.2 Test case development | 0.5 | 13.02.25 | 13.02.25
|  |  | 5.3.3 Test case execution | 0.5 | 14.02.25 | 14.02.25
6 | Deployment | 6.1 Deploy the package as 1GP | 6.1.1 Create namespace for the package | 0.5 | 14.02.25 | 14.02.25
Week 5
|  |  | 6.1.2 Deploy the 1 GP package | 1 | 17.02.25 | 17.02.25
|  |  | 6.1.3 Fix, Manage Dependencies, Components | 1 | 18.02.25 | 18.02.25
7 | Submission |  |  | 21 | 26.02.25 | 26.02.25